...COLUMNWIDTH 45
                         Programminç the

       Performance Evaluation and Review Ôechnique (PERT)

                            in BASIC
                              

            "Á method for planninç complex activities 
                   where no precedentó exist."

     Originaì program by Steven Zimmerman and Leo M. Conrad
     Developed and modifieä for the Osborne 1 by Doug Hurst

               Texô and program listinç reprinteä 
               from BYTE Magazine with permission.



                        TABLE OF CONTENTS



           Osborne 1 Prolog . . . . . . . . . . .    2
           Introduction.  . . . . . . . . . . . .    3
           Origins oæ PERT. . . . . . . . . . . .    3
           The Start oæ PERÔ Analysis.  . . . . .    3
           The Bubble Diagram.  . . . . . . . . .    4
           The Critical Path. . . . . . . . . . .    4
           Three Time Estimates.  . . . . . . . .    5
           Our PERT Program.  . . . . . . . . . .    5
           Runninç the Program. . . . . . . . . .    6
           Conclusion.  . . . . . . . . . . . . .    8
              Figure 1  . . . . . . . . . . . . .    9
              Tablå 1 . . . . . . . . . . . . . .   10
              A Glance at the Mathematicó of PERT   11




















                    Programming PERT iî BASIC

            "A method foò planning complex activities 
                   wherå no precedents exist."

     Original program bù Steven Zimmerman and Leï M. Conrad
     Developed anä modified for the Osbornå 1 bù Douç Hurst

               Text and program listing reprinted 
               from BYTE Magazinå witè permission.


...T1
Osborne ± Prolog
     The BYTE article from which this librarù submission waó 
extracted appearó on pages 465-478 oæ the May 1982 issue with the �
theme "Japanese Computers. 
     This was á fairly easy prograí to convert to run on thå O-1 
as are most programs writteî in TRS-8° Level II or Disk 
Basic(alsï by MicroSoft)® Deletionó to the prograí include all 
tape save and load routines. Additions include a means by which �
to designate time units used and project start dates as well as 
their appearance on thå harä copù output. Also, and most �
important, is the inclusion of thå ability to display and �
printout a GANNT Chart of thå pertinenô PERÔ elements.
     Thå program has great practical utility.  At thå Marine 
Corpó Communication-Electronics School, Twentyninå Palms, CA, we 
arå involved in a largå number oæ courseware conversions (to 
Computer Aided Instruction(CAI)) that are spread out, in some 
cases¬ oveò periods as large aó years. PERT has been instrumental 
in both the planning and monitoring oæ these projects.
     There are now 3 main programs oî the diskette, PERTSAMP.COM, �
PERT80.BAS, and PERT128.BAS. PERTSAMP.COM ió somethinç I'm really 
proud of, although I can'ô takå fulì credit for thå originality. �
I pulled a program called OSBOARD1.COM off Kelly Smith's CP/M Net 
á while back. Iô was really an advertisement for a program which �
makes thå O-1's graphicó easù to use. In doing sï it showeä the 
program's capability. PERTSAMP.COM does much thå same. Just place 
the PERT diskette iî the A drive and hiô the return. 

IMPORTANT ! Make sure you printeò is up when yoõ do so. 

What yoõ wilì get is a complete samplå run of the PERT program 
including printouts. You should do this right away even though 
PERT hasn't even been explained yet.  The ´ pages of output arå 
Listings 2,3,4,and 5 as referreä to in thå article proper. 
PERTSAMP ió compiled BASIC. PERT80/128.BAS arå named based oî 
their printer requirements® TEMÐ is merelù a file which you may 
read into the program for practice.
     Witè the latest addition, that is- the GANNÔ Chart, this 
PERT program ió swiftly approachinç the quality oæ MILESTONÅ (on 
thå Osborne Approved Software list: Organiã Software¬ Retail 
Pricå $295.00)® 



(Noteº My friend, foò the time being, Jerry Lawson¬ has been 
ploddinç awaù at PERT'ó companioî program "Programming thå 
Critical Path Method in BASIC", (BYTE, July 1982, pages 378-390) 
for quite some time now. I forced him tï do it because so much 
can be learned abouô programing from thå copying and debugging 
process. It's been á slo÷ process and besideó he has a wife and �
family tï which he is more devoteä thaî his Osborne. Can't 
understand that. When he finisheó his part¬ the program will bå 
cleaneä up, modified and submitted. Once this is done, MILESTONE 
will have been equaled.) 

...T1
Introduction.
     The Performance Evaluation and Revie÷ Techniquå (PERT) ió a 
powerful methoä of planning compleø activities, especially �
pioneering projectó likå the creation of a new business or the �
development oæ a new machine® The innovativå nature oæ these 
projects assureó thaô few precedentó exist to help estimate �
performance time.
     PERT giveó managers the tools to deal with uncertainty» PERÔ 
ió management in action.  It plans, schedules, and controls 
activity. Usinç PERT, contractors, builders, engineers¬ and 
businessmen can improvå planning in the midst oæ uncertainty and 
save money as a result.
     Until now, only largå businesses with access to large 
computers coulä use PERT® The program iî listing ± (Listing 1 maù 
bå obtained by loadinç either PERT80.BAS or PERT128.BAS, setting 
WIDTÈ LPRINT 80, anä theî doing a LLIST.) brings PERT'ó power to 
microcomputeò users. 
     Before presenting our program¬ however, we'lì givå you a 
glimpse at PERT's history¬ briefly describe the nature of PERT 
analysis, suggest onå possible PERT application foò a manager, 
and examinå the mathematics behind PERT.

...T1
Origins of PERT.
     PERT dateó bacë to á teaí created by thå Navù Special �
Projects Office, Lockheed Aircrafô Corporation, and management �
consulting firm of Booz¬ Allen, and Hamilton. Work during World 
Waò I oî the Gannô scheduling chart and thå Gannt milestone chart 
should also be noteä because these precipitated the development �
of the networë diagram (described later) used in PERT.
     Manageró of many different kinds of tasks have successfully 
applied PERT. One particularly spectacular result of thå PERÔ 
approach is the Polaris missile¬ which also occasioned PERT's 
development. (Lockheed Aircraft was the major contractor for 
Polaris.) Completioî timå was critical in thå Polaris program, 
but there was considerable uncertainty about how long the 
required activities woulä take.  Moreover, the start oæ manù 
activities depended oî the completioî of others. These are thå 
chief reasons whù PERÔ employs á network schemå and focuses oî 
the probability of various activitieó finishinç at specified �
times.

...T1
The Start of PERT Analysis.
     PERT analysis begins by reducing a project description to a �
lisô of eventó and activities.  Aî activity is a part of a 
project that consumes resources or time anä has a definable 
beginning and end. Aî event is a point iî time, instant® The 
beginning anä ending points of aî activity are events. To applù 
PERT tï a compleø project, you must identify all thå events 
needed to complete the projecô and all the activities that resulô 
iî the identifieä events.
     As aî example, we'lì use a simplified versioî of an actual �
construction project that we just completed® To simplify, we'll 
enä our example with the completion oæ the building'ó foundation. 
We identified 18 activities needed to complete this foundation. �
Table 1 lists the activities¬ assigned letters A through Q and Z. 
Each of thå ninå events iî the project consists of the completion 
of one or more activities.

...T1
The Bubblå Diagram.
     Thå second stage in PERT analysió is the layout of a 
"bubble¢ diagram that shows how the necessary activities and 
events form a sequence oæ steps. Figure 1 is the bubblå diagram �
of our foundation-building example. With or without PERT, �
specifying thå sequence of a project's stepó is obviously an 
important planning activity. Most contractors lay out the 
sequence oæ tasks in a project in some fashion, buô PERÔ makes 
task sequencing a formal activity. Formalizinç thió process lends 
valuablå structurå to essential planning. In particular, makinç a 
bubble diagram forces thå planner to specify whicè activities 
depenä on the completion of others.


     Diagrams like that shown in figure 1 arå alsï called 
networks. A PERT network has one initiaì event, aô the extreme 
left¬ and one terminal event, at the extreme right. thå circles �
in figurå 1 (after you perform a littlå artwork) are numbered and 
represent events. Thå lines arå lettered and represent �
activities; each line has an arro÷ indicating itó directioî in �
timå froí beginninç to completion® The network aó a whole shows 
thå series oæ activities that must be performed to complete thå 
project. thå arrows show which activities and eventó logicallù 
precedå others.
     An event that results from completion oæ morå thaî one 
activitù is calleä a merge event» an event that representó the 
joint beginning oæ morå thaî one activity is called á burst 
event® Before any activitù can start, alì precedinç activities 
must be completed (but noô all simultaneously). An arrow's length 
anä its compass direction are insignificant.
     Dashed lineó in network diagramó represenô 
"dummy"activities. A dummy activity existó wheî the completioî of �
one evenô depends on thå completion of another but requireó no �
additional work or activity. PERT handles dummy activities like 
anù others but assigns the activity zero time and zero costs.

...T1
The Critical Path.
     The longest route from the beginning oæ the network oî the 
left to its end oî the righô determines thå timå required to 
complete the project. this line is the critical path, which 
determines the minimum time required to completå a job. Although 
the concepô of á critical path may sound complex, it is simple 
once you'vå laiä a projecô out in a bubble diagram.
     Critical-patè analysis can reveaì wayó to shorten thå 
critical path anä to control thå total length of a job. Because 
of thå sizå of our computer, this prograí analyzes the critical 
path but does not attempô to shorten it.

...T1
Three Time Estimates.
     Along each activitù linå in figurå 1, you see three decimaì 
numbers. These numberó represenô an optimistic¬ likely and 
pessimistiã estimate of the time requireä to complete the 
activity. Each time the activity is not on thå critical path¬ a 
manager's decision to authorize expenditures for overtime would �
be foolish anä wasteful® All activitieó not on the criticaì patè 
have "slack time," thå difference between the earliest and latest �
expected finish. Bù definition, only the activities oî the 
criticaì patè havå zerï slack time. We'll elaborate later.

...T1
Ouò PERÔ Program.
Ouò PERÔ Program is shown iî listing 1. A dimension (DIM) 
statement at line 160 provides places to store data on 
activities® The same DIM statement also provides storagå for a 
dummy variable,SV, tï be used later during sorts.
     On a system with 32Ë (remembeò the article was written for á 
TRS-80© bytes of memory anä two disk drives, our program can �
handle more than 200 activities. We have yeô to need more than �
100 activities. Your machine's memory capacity and thå limits oæ 
your DIM statement will determine thå sizå of the probleí thaô 
our program can handlå for you. You can find the limits by 
experimentation.
     Onå way to save memory is tï carefullù omiô remark (REM) �
statements(These statements are left iî in fn.ft PERTSAMP.BAS but 
have been removed from PERT80.BAS and PERT128.BAS in thå Osborne �
1 version). 
     As noted before, thå critical path consists of a serieó of �
activities that have zero slack time. To find thå critical path¬ 
you must identifù activities that have zero slack time. The 
program output¬ consisting of two tables, is designed to identifù 
these activities.
     Thå first table (see listinç 2) shows the program's input¬ 
listinç all the activities in the project¬ their beginning anä 
ending events, and thå three estimates of the time each activity 
requires. You shoulä check your input whenever yoõ use this 
program because otherwise you maù get crazù results.
     The second table (see listinç 3) is thå program'ó output. �
Notice the last column, "Slack Time." Zeros in this column 
identifù the critical path. You can, of course, tracå the 
activities iî the critical path by looking in the first column¬ 
"Code,¢ for each activity with zero slack time® But our program 
also provides a menu option CRITICAÌ PATÈ AND TIME¬ which permits 
both thå critical path and the time required to complete it. 
     Familiarity with thå project and the program will probably �
makå listings 2 anä 3 all yoõ wilì neeä to fully monitor you 
program.  Unfortunately, many times therå wilì be á neeä to make �
the schedulinç of your project understandable to supervisors or 
others without detaileä explanation. This is where listinç 4 
becomes invaluable. Listing 4 is a GANNÔ chart foò the project. �
Thió chart caî be headeä in eitheò one of two ways depending on 
thå timå estimateó in your DATA statements® Thió wilì be eitheò 
WEEKS or MONTHS. The GANNT charô header ió triggereä by you input �
on line 150. If yoõ enter WEEKS your header will show 15 months 
of 4 weeks each oî PERT80 and 2 years of weeks on PERT128® If you 
pick MONTHS, you geô 5 years of months on either PERT8° or �
PERT128. The GANNT Charô lists each activitù similar to listingó 
2 and ³ and actually merelù provides a graphic representation of 
listing 3®  Thå E represents the early start time® The @ and/or Ã 
symbol represent the expected time for thå activity (C's if the 
activity ió on the Critical Path). The L is for thå lasô finish. �
By  default, any space between thå lasô @ for an activity and the 
Ì represents slack time iæ the activity is started at the early 
starô and is finished in the expected time. There will be nï 
space between thå lasô C and thå L for anù activity® As stated, 
these lie on thå critical path and there is nï slack time. 
     A word of caution about using the program: round-off 
problems in calculation the critical path forced us to define 
zero slack time as 0.001 instead of true zero® Where small 
differences arå important, this approximatioî of zero can cause �
problems® The valuå 0.001 is entered iî linå 1490; perhaps you �
can change thå value to true zero for some of your applications® 
Furthermore¬ since we used statistical methods to determine the 
probabilitù of á project'ó being completed on time¬ given a �
scheduleä completion date, you should remember that data 
generated by the program is based on estimates anä is itselæ an �
estimate.

...T1
Running the Program.
     The easiest waù to input data is tï use DATA statementó at �
the end of thå program starting always at line number 4000® 
Entering data from thå keyboard takeó timå and increases the �
number oæ errors.  The best way dï the DATA statementó is to boot 
up WordStaò in drive A anä the PERT diskette in drive B® Create a 
file on drivå B iî the "N" non-document mode that pretty well �
discribeó youò project. Like "BUILDING.BAS"® Simply start using 
line 4000 with thå number oæ activities anä the number of events. 
Then add each activity letter¬ description,starting anä ending 
evenô and lastly thå optimistic, likely¬ and pessimestic times, �
as below:

4000 DATA 18,9
4010 DATA A,ACCT. PAPERS,1,2,1,2,3
402° DATÁ B,SHOP BANKERS,1,3,2,4,6
4030 DATA C,SHOP REAL EST.,1,4,1,13,17
ETC......

Once this is done, save the program. No÷ booô up MBASIÃ and LOAD 
"x:PERT80" oò "x:PERT128". MERGE "x:BUILDING" tï append your DATA 
lineó to the prograí theî SAVÅ "x:BUILDING" (x: = the disk drive 
of choice). This saves the entirå program under the name formerly 
used by your DATA lines and leaves PERT80/12¸ intact withouô datá 
lines and available for future projects. The following Šdescription of a program run assumes that DATA statements were 
used for input.
     Whether you input data from DATA statementó or the keyboard, 
the program begins by giving the identification messagå and then 
displays:

                  *** NOTE BEGINNING EVENTS 
                      WILL BÅ SORTED INTO                       
NUMERICAL ORDER ***

when asking

                   DIMENSIONS FOR ACTIVITIES?_
(NOTE: This will only appear if data is tï be entered from 
keyboard or disk file.)

                    TIMÅ UNITS WILL BE MEASURED IN?_
and
                    PROJECT START DATE?_

     As yoõ see in listinç 2, eventó are arranged according to 
the earliest startinç event in each activity, and ties are broken 
by reference to the earliesô ending event for each activity.
     Now the program presents the input menu:

                           INPUÔ MENU
 
                           K KEYBOARD
                           D DISK FILE

     Option R causes thå program to read DATA statements aô the 
enä of the program. After a brieæ delay, the program will display 
for verification thå input of what was read.
     The videï display of thå input will look slightlù differenô 
than the table iî listing ² because of thå differences iî the 
screen and printeò sizes. Iæ a single screen won't accommodate 
alì the input, thå program will ask you to page through.
     Afteò listing all the input, the prograí wilì say:

          -2 ADD, -1 TO CONTINUE OR NUMBER TO CHANGE?_

Thå number referred to is the number of anù activity that you �
wisè to change.  Assuming yoõ wanô to continue and enter -1, thå 
prograí wilì ask:

                 HARÄ COPÙ OF INPUT DATA (Y/N)?_

If you requesô harä copy, thå program will print 3 lines oæ EGO 
data anä theî asks:
                             TITLE?_
                             DATE?_

and will print your responses¬ as well as thå measure of time 
units at the toð of the page. Our sample set of data used thå 
title PERT SAMPLÅ and the date 11/26/82.Š     Afteò the inpuô is printed, the screen will display thå 
results, as showî in listing 3. For each activity, you will see 
computations of how long it should be expecteä to take, the �
earliest week (you may use months also© it can start, the �
earliest it can finish, and the slack time (the difference 
between the earliest and latest possible finish). Yoõ may have to 
page through a screen display of this data. The prograí wilì 
again ask iæ you want hard copy.
     Next thå GANNT Chart will bå displayeä witè paging again if 
necessary and a prompt foò harä copy. Lines 8µ and 90 set screen �
and printer width to accomodate all requirements.

     Then you will see:
                              OUTPUÔ MENU

                          C CRITICAÌ PATÈ AND TIME
                          D DISK
                          E END
                          Ò RECYCLE

                          SELECTION?_

Option C, for ouò example, results iî a displaù likå the 
following:

CRITICAL PATH

C I K Î P

TIMÅ OF CRITICAL PATH
42.33
SCHEDULEÄ PROJECT TIME (USE SAME TIME UNITS AS DATA)?_

     For our example¬ the critical path consists oæ shopping for �
a real-estate agent, obtaining land, gettinç architectural plans, 
getting a detailed layout for construction, and actuallù building 
thå foundation. The time of the critical path ió expected to bå 
42.33 weeks® 
     You caî now inpuô the scheduled time for the project, anä 
the program will use the Z calculations explained iî the textbox 
"A Glance at the Mathematics of PERT" tï telì you a probability �
of meeting thå schedule® As shown in listinç 3, there is a 
0.0123852 probability of finishing in 35 weeks and a 0.990536 �
probability oæ finishinç in 50 weeks. As noted earlier, there ió 
also a .500 probability of finishing in the expecteä timå of the 
critical path - 42.33 weeks.

...T1
Conclusion.
     If yoõ neeä helð planning and scheduling complex projects, 
this PERT program can provide it. You can uså it without knowing 
ho÷ to perform thå calculations involved. Although wå repeat our 
caution about relyinç on estimate-based estimates, we still �
believe PERT has proved itself a valuable managerial tool and 
that our program accurately represents PERT.

           ß                                  _
          |2|                                |7|
                                                      _ 
                                                     |8|  

                                                              _
  _                _                  _                      |9|
 |1|              |3|                |5|
  


                          _                     _
                         |4|                   |6|   


(NOTE: Since it is impossiblå to draw á fulì fledged bubblå diagram with �
WordStar¬ perform the following upon printing this documentation. Connect the �
bubbles and label the resultant lines as shown below.

             1-2  A-1,2,3             4-5  I-8,11,13
             1-3  B-2,4,6             5-6  J-2,3,4
             1-´  C-2,13,17           5-·  K-2,5,12
             2-3  D-2,4,5             5-8  L-1,2,4
             2-µ  G-1.4,2.2,6.·       6-¸  M-2,3,4
             2-6  F-.4,1.3,1.5        6-9  O-1,2,5
             2-7  Z-4,5,8             7-8  N-9,11,12
             3-4  E-3,4,5             7-9  Q-1,2,3
             3-µ  H-2,4,6             8-¹  P-1,3,6
 
...T2
Figure 1
     The PERT network diagram oæ the activitieó required to build á foundation. 
Each circle represents aî event anä eacè linå between circles represents one of 
thå activities listed in table 1® The threå numbers given for each activity 
represent humaî estimateó of the optimistic(minimum), likely, anä 
pessimistic(maximum) time in weeks that each activity will take. The network has �
one initial event, evenô 1 aô the extreme left and onå terminal event, event 9 
at the extreme right. The critical path is the one that takes the most time tï 
get from event 1 to event 9.

















Letter    Activitù                   Beginning     End
                                       Event      Event

   
  Á       assemblå accounting data      1           2
  Â       look foò banë                 1           3
  Ã       look foò real-estate agent    1           4
  Ú       seek permits                  2           7
  Ä       make market study of area     2           3
  Ç       look foò contractor           2           5
  Æ       seek insurance foò con-       2           6
          struction
  H       get basic architectural plans 3           5
  E       make cost study               3           4
  I       buy land                      4           5
  J       list materials                5           6
  K       get more detaileä architec-   5           7
          tural plans
  L       havå survey made              5           8
  M       buy firsô batch of materials  6           8
  O       buy second batch oæ           6           9
          materials
  Î       completå detailed internal    7           8
          layout of foundation
  Q       hire crew                     ·           9
  P       build foundatioî              ¸           9

...T2
Table 1
The activities required tï build a foundation® the program iî listing ± useó the 
letters at left tï identify the activities® The two columns at righô lisô the 
first and last event during each activity. An event is thå completion of one or 
more activities.























...T2
A Glance at the Mathematics of PERT

     The mathematics of PERT involves some interestinç 
statistical concepts. You don't have to understand the 
mathematics to use PERT, but it helps you to understanä how our �
program works.
     First, we must refresh your recollection oæ somå basic 
statisticaì terms. the mean of a seô of occurences of some 
variable is thå arithmetic average of the values of thå 
occurences; the standard deviation ió the square root of the mean �
of the squareó of the deviations of individual occurences from �
the mean); thå variance is the square of thå standard deviation.
     Foò example, if wå havå three values 9.12 and 15, their mean 
is 36/3=12, their variance is

(9-12)² + (12-12)2 + (15-12)2 = 18

and the standard deviation ió the square root of 18, which is 
approximately 4.24.
     It is a commoî statistical assumption that the standard 
deviation in unimodaì distributions (distributions that have only 
a singlå most-likely occurring value) is roughlù a sixth of thå 
range of distribution lies with threå standard deviationó of the 
mean» and for the normal distribution, 99.7 percent of the �
distribution lies withiî three standarä deviations of the mean.
     Since we have estimates of the minimum time  a  and the 
maximum time  b  required to complete an activity, we have 
established an estimated rangå of actuaì times. Wå can estimate �
the standard deviation of thå actual time as

                              (b-a)
                                6

     Sincå PERÔ assumes that chance, or random factors will 
influence thå actual time needed to complete an activity, we can 
expecô the actual times tï be distributeä along some curve. PERT �
assumes that the mean actual time will follow thå distribution �
known as the beta distribution, which is contained in a finite �
interval and may bå either symmetric oò skewed. Our most likely 
time of completioî  m  is the mode of the curve for each �
activity® the following equation, baseä on the assumption that �
our formula for thå standard deviation is correct, is linear 
approximation oæ the valuå of the expected value, EV, oæ the mean 
time:

                              (a+4xm+b)
                         EV = ----------
                                  6

Aó you can see, this is just a weighted average, countinç the 
minimum and maximum each once anä the mode four times, then 
dividing the total bù 6. On line 99° of listing 1, same equation �
is expressed as:

                A(I,6)=(A(I,3)+4*A(I,4)+A(I,5)/6

     The following equatioî gives thå variance of the beta 
distribution foò eacè activity:

                         VAR =((b-a)/6)2

     For each activity, thå program applies thå statistical 
principleó describeä above anä calculates thå timå the activity �
should last, the earliest time at whicè it can start, the �
earliest finish, the latest start¬ and the latesô finish. �
Calculation oæ the earliest start and finisè times is called thå 
"forward pass" and takes place in ouò program at lines 970 to 
1080. Calculation of the latest start and finisè is calleä the 
"backward pass" and takes place at lines 1090 tï 1230.
     The difference betweeî the earliest and latest projected 
finish for each activity is called "slack time"® At lines 1240 to 
1290¬ the program calculates slack time for each activity. The 
evenô thaô havå zerï slack time form thå critical path.
     To obtain thå approximate variance foò the critical path, 
adä the variances of the activities oî the path:

               VAR(Path)=VAR(1)+VAR(2) ....+VAR(n)

Iô happens that the Centraì Limit theorem enables us, based oî 
the foregoing, tï assume that the distribution of the time 
required tï complete the critical path ió normal. Based on this 
assumption, we can calculate the probability of the project's 
being on time, given some specified target completion time. The 
calculation's basis is the deviation of the scheduled completion 
time from thå estimateä meaî completion with thå deviatioî 
measured in unitó of standard deviations. This deviation is 
called Z. The Ú calculation for thå standard normal table is:

                 (scheduled             time of  )
                 ¨   time           critical path)
             Z ½ ----------------------------------
                            VAR(Path)

     Rather than require you to use normaì tables with our 
program, wå havå built in a Taylor serieó to approximatå the 
tables. (A Taylor series is a power series that giveó the 
expansion of a functioî  f(x)  iî the neighborhood oæ a point a, 
provided all derivatives exist and á series converges.) The �
Taylor series is locateä at line 2440 and following iî our 
program.
     Thå expected time of the criticaì patè is the sum of the �
expected timeó of all the activities oî the path® If the 
scheduled time of the project equals thå expected time of the 
critical path, you have a 50 percenô chance oæ completing thå 
projecô on time.